## Summary
Sparsh Magic HRMS - Phase 1 FRD v1.1: Build Status
Source: 'Sparsh_Magic_HRMS_Phase1_FRD_v1_1_Configurable_Fields_Rules_Policies.pdf'. Status = HRMS code at commit 5cffdc2 plus the work of 24 Oct 2026 (marked NEW / DONE, not yet committed).
Legend: Built = in place and tested; Partially Built = exists with a stated gap; Missing = not built; Pending Client Decision = FRD leaves the value open.
FRD Section | Built | Partially Built | Missing | Pending Client Decision | Total | % Built
3. Employee Information
4. Employee Creation / Change Process
5. Attendance Configuration
6. Daily Attendance Fields
8. Attendance Processing & Monthly Closure
9. Salary Structure Fields
10. Monthly Payroll Input
11. Payroll Calculation Logic
12. Payroll Approval Workflow
13. Salary Disbursal
14. Payslip
16. Core Data Relationships
17. Roles & Access
18. Validation & Control Requirements
20. Phase 1 Acceptance Criteria
21. Cross-Module Configurability
22. Configurable Field Management
23. Attendance Policy & Rule Configuration
24. Salary Component Configuration
25. Formula / Calculation Rule Engine
26. Policy Versioning & Effective Dates
27. Configuration Change Approval Flow
29. Administrative Screens
30. Configurability Acceptance Criteria
TOTAL

## FRD Field Status
FRD Field Status - every field / requirement in the FRD
Filter column E to see Missing or Partially Built items. Column G explains what exists or what is missing.
# | FRD Section | Group | Field / Requirement (as in FRD) | Build Status | Where in System | What Exists / Gap
1 | 3. Employee Information | Basic Identity | Employee ID / Code | Built | HRMS > Employees > Employee profile (Job / Personal tab) | Auto-numbered EMP-YYYY-NNN per company
2 | 3. Employee Information | Basic Identity | First Name | Built | HRMS > Employees > Employee profile (Job / Personal tab)
3 | 3. Employee Information | Basic Identity | Middle Name | Built | HRMS > Employees > Employee profile (Job / Personal tab)
4 | 3. Employee Information | Basic Identity | Last Name | Built | HRMS > Employees > Employee profile (Job / Personal tab)
5 | 3. Employee Information | Basic Identity | Display Name | Built | HRMS > Employees > Employee profile (Job / Personal tab)
6 | 3. Employee Information | Basic Identity | Photograph | Built | HRMS > Employees > Employee profile header | Photograph is a profile field with upload / replace / remove; falls back to the 'Photograph' document.
7 | 3. Employee Information | Personal | Date of Birth | Built | HRMS > Employees > Employee profile > Personal
8 | 3. Employee Information | Personal | Gender | Built | HRMS > Employees > Employee profile > Personal
9 | 3. Employee Information | Personal | Marital Status | Built | HRMS > Employees > Employee profile > Personal
10 | 3. Employee Information | Personal | Blood Group | Built | HRMS > Employees > Employee profile > Personal
11 | 3. Employee Information | Personal | Nationality | Built | HRMS > Employees > Employee profile > Personal
12 | 3. Employee Information | Contact | Personal Mobile | Built | HRMS > Employees > Employee profile > Contact & Address | Format validated; duplicate check on email / mobile
13 | 3. Employee Information | Contact | Official Mobile | Built | HRMS > Employees > Employee profile > Contact & Address | Format validated; duplicate check on email / mobile
14 | 3. Employee Information | Contact | Personal Email | Built | HRMS > Employees > Employee profile > Contact & Address | Format validated; duplicate check on email / mobile
15 | 3. Employee Information | Contact | Official Email | Built | HRMS > Employees > Employee profile > Contact & Address | Format validated; duplicate check on email / mobile
16 | 3. Employee Information | Current Address | Address Line 1 | Built | HRMS > Employees > Employee profile > Contact & Address | PIN validated as 6 digits for India
17 | 3. Employee Information | Current Address | Address Line 2 | Built | HRMS > Employees > Employee profile > Contact & Address | PIN validated as 6 digits for India
18 | 3. Employee Information | Current Address | City | Built | HRMS > Employees > Employee profile > Contact & Address | PIN validated as 6 digits for India
19 | 3. Employee Information | Current Address | District | Built | HRMS > Employees > Employee profile > Contact & Address | PIN validated as 6 digits for India
20 | 3. Employee Information | Current Address | State | Built | HRMS > Employees > Employee profile > Contact & Address | PIN validated as 6 digits for India
21 | 3. Employee Information | Current Address | PIN Code | Built | HRMS > Employees > Employee profile > Contact & Address | PIN validated as 6 digits for India
22 | 3. Employee Information | Current Address | Country | Built | HRMS > Employees > Employee profile > Contact & Address | PIN validated as 6 digits for India
23 | 3. Employee Information | Permanent Address | Address Line 1 | Built | HRMS > Employees > Employee profile > Contact & Address
24 | 3. Employee Information | Permanent Address | Address Line 2 | Built | HRMS > Employees > Employee profile > Contact & Address
25 | 3. Employee Information | Permanent Address | City | Built | HRMS > Employees > Employee profile > Contact & Address
26 | 3. Employee Information | Permanent Address | District | Built | HRMS > Employees > Employee profile > Contact & Address
27 | 3. Employee Information | Permanent Address | State | Built | HRMS > Employees > Employee profile > Contact & Address
28 | 3. Employee Information | Permanent Address | PIN Code | Built | HRMS > Employees > Employee profile > Contact & Address
29 | 3. Employee Information | Permanent Address | Country | Built | HRMS > Employees > Employee profile > Contact & Address
30 | 3. Employee Information | Permanent Address | Same-as-current flag | Built | HRMS > Employees > Employee profile > Contact & Address
31 | 3. Employee Information | Emergency Contact | Contact Name | Built | HRMS > Employees > Employee profile > Contact & Address
32 | 3. Employee Information | Emergency Contact | Relationship | Built | HRMS > Employees > Employee profile > Contact & Address
33 | 3. Employee Information | Emergency Contact | Mobile | Built | HRMS > Employees > Employee profile > Contact & Address
34 | 3. Employee Information | Emergency Contact | Alternate Number | Built | HRMS > Employees > Employee profile > Contact & Address
35 | 3. Employee Information | Employment | Date of Joining | Built | HRMS > Employees > Employee profile > Job & Organisation
36 | 3. Employee Information | Employment | Employee Category | Built | HRMS > Employees > Employee profile > Job & Organisation
37 | 3. Employee Information | Employment | Employment Status | Built | HRMS > Employees > Employee profile > Job & Organisation
38 | 3. Employee Information | Employment | Probation Start | Built | HRMS > Employees > Employee profile > Job & Organisation
39 | 3. Employee Information | Employment | Probation End | Built | HRMS > Employees > Employee profile > Job & Organisation
40 | 3. Employee Information | Employment | Confirmation Date | Built | HRMS > Employees > Employee profile > Job & Organisation
41 | 3. Employee Information | Organisation | Company / Legal Entity | Built | HRMS > Employees > Employee profile > Job & Organisation | Dropdown values maintained in Employee Master Setup
42 | 3. Employee Information | Organisation | Business Unit / Branch | Built | HRMS > Employees > Employee profile > Job & Organisation | Dropdown values maintained in Employee Master Setup
43 | 3. Employee Information | Organisation | Location | Built | HRMS > Employees > Employee profile > Job & Organisation | Dropdown values maintained in Employee Master Setup
44 | 3. Employee Information | Organisation | Department | Built | HRMS > Employees > Employee profile > Job & Organisation | Dropdown values maintained in Employee Master Setup
45 | 3. Employee Information | Organisation | Sub-department (if used) | Built | HRMS > Employees > Employee profile > Job & Organisation | Dropdown values maintained in Employee Master Setup
46 | 3. Employee Information | Job | Designation | Built | HRMS > Employees > Employee profile > Job & Organisation
47 | 3. Employee Information | Job | Grade | Built | HRMS > Employees > Employee profile > Job & Organisation
48 | 3. Employee Information | Job | Level | Built | HRMS > Employees > Employee profile > Job & Organisation
49 | 3. Employee Information | Job | Job Title | Built | HRMS > Employees > Employee profile > Job & Organisation
50 | 3. Employee Information | Job | Cost Centre | Built | HRMS > Employees > Employee profile > Job & Organisation
51 | 3. Employee Information | Reporting | Reporting Manager Employee ID | Built | HRMS > Employees > Employee profile > Reporting | Effective-dated; history kept
52 | 3. Employee Information | Reporting | Reporting Manager Name | Built | HRMS > Employees > Employee profile > Reporting | Effective-dated; history kept
53 | 3. Employee Information | Reporting | Functional Manager (if applicable) | Built | HRMS > Employees > Employee profile > Reporting | Effective-dated; history kept
54 | 3. Employee Information | Work Configuration | Work Location | Built | HRMS > Employees > Employee profile > Work Setup
55 | 3. Employee Information | Work Configuration | Shift / Timing Group | Built | HRMS > Employees > Employee profile > Work Setup
56 | 3. Employee Information | Work Configuration | Attendance Policy Group | Built | HRMS > Employees > Employee profile > Work Setup
57 | 3. Employee Information | Work Configuration | Weekly-Off Pattern | Built | HRMS > Employees > Employee profile > Work Setup
58 | 3. Employee Information | Work Configuration | Holiday Calendar | Built | HRMS > Employees > Employee profile > Work Setup
59 | 3. Employee Information | Bank | Bank Name | Built | HRMS > Employees > Employee profile > Statutory & Bank | Account number / PAN masked for viewers without salary access
60 | 3. Employee Information | Bank | Branch | Built | HRMS > Employees > Employee profile > Statutory & Bank | Account number / PAN masked for viewers without salary access
61 | 3. Employee Information | Bank | Account Holder Name | Built | HRMS > Employees > Employee profile > Statutory & Bank | Account number / PAN masked for viewers without salary access
62 | 3. Employee Information | Bank | Account Number | Built | HRMS > Employees > Employee profile > Statutory & Bank | Account number / PAN masked for viewers without salary access
63 | 3. Employee Information | Bank | IFSC | Built | HRMS > Employees > Employee profile > Statutory & Bank | Account number / PAN masked for viewers without salary access
64 | 3. Employee Information | Bank | Account Type | Built | HRMS > Employees > Employee profile > Statutory & Bank | Account number / PAN masked for viewers without salary access
65 | 3. Employee Information | Bank | Effective From | Built | HRMS > Employees > Employee profile > Statutory & Bank | Account number / PAN masked for viewers without salary access
66 | 3. Employee Information | Statutory / Payroll IDs | PAN | Built | HRMS > Employees > Employee profile > Statutory & Bank
67 | 3. Employee Information | Statutory / Payroll IDs | UAN / PF | Built | HRMS > Employees > Employee profile > Statutory & Bank
68 | 3. Employee Information | Statutory / Payroll IDs | ESI | Built | HRMS > Employees > Employee profile > Statutory & Bank
69 | 3. Employee Information | Statutory / Payroll IDs | Other approved statutory identifiers | Built | HRMS > Employees > Employee profile > Statutory & Bank / Additional fields | Passport and Driving Licence built; any further identifier can be added as a sensitive configurable field. The FRD gives no further list.
70 | 3. Employee Information | Salary Linkage | Salary Structure / Template | Built | HRMS > Employees > Employee profile > Salary | CTC / Gross read from the active salary structure
71 | 3. Employee Information | Salary Linkage | Payroll Group | Built | HRMS > Employees > Employee profile > Salary | CTC / Gross read from the active salary structure
72 | 3. Employee Information | Salary Linkage | Effective Date | Built | HRMS > Employees > Employee profile > Salary | CTC / Gross read from the active salary structure
73 | 3. Employee Information | Salary Linkage | Annual CTC | Built | HRMS > Employees > Employee profile > Salary | CTC / Gross read from the active salary structure
74 | 3. Employee Information | Salary Linkage | Monthly Gross | Built | HRMS > Employees > Employee profile > Salary | CTC / Gross read from the active salary structure
75 | 3. Employee Information | Documents | PAN | Built | HRMS > Documents / Document Types
76 | 3. Employee Information | Documents | Aadhaar | Built | HRMS > Documents / Document Types
77 | 3. Employee Information | Documents | Bank Proof | Built | HRMS > Documents / Document Types
78 | 3. Employee Information | Documents | Address Proof | Built | HRMS > Documents / Document Types
79 | 3. Employee Information | Documents | Photograph | Built | HRMS > Documents / Document Types
80 | 3. Employee Information | Documents | Education | Built | HRMS > Documents / Document Types | Seeded as 'Degree Certificate'
81 | 3. Employee Information | Documents | Previous Employment | Built | HRMS > Documents / Document Types | Seeded as 'Experience Letter' / 'Relieving Letter'
82 | 3. Employee Information | Documents | Appointment Letter | Built | HRMS > Documents / Document Types | Seeded as a candidate document; HR can set it to apply to employees
83 | 3. Employee Information | Documents | PSC | Built | HRMS > Documents / Document Types | DONE 24 Oct: 'PSC' document type seeded for new companies and offered once to existing ones.
84 | 3. Employee Information | Documents | Other approved categories | Built | HRMS > Documents / Document Types | HR can create any document type under any category. The FRD does not list the approved categories.
85 | 3. Employee Information | System / Audit | Active / Inactive | Built | HRMS > Employees > Employee profile (footer) / History tab | Derived from login status + employment status
86 | 3. Employee Information | System / Audit | User Account | Built | HRMS > Employees > Employee profile (footer) / History tab | Profile linked to the login account
87 | 3. Employee Information | System / Audit | Role | Built | HRMS > Employees > Employee profile (footer) / History tab | From the user account
88 | 3. Employee Information | System / Audit | Effective From / To | Built | HRMS > Employees > Employee profile (footer) / History tab | DONE 24 Oct: employee history shows Effective From and Effective To (day before the next change).
89 | 3. Employee Information | System / Audit | Created By / Date | Built | HRMS > Employees > Employee profile (footer) / History tab
90 | 3. Employee Information | System / Audit | Modified By / Date | Built | HRMS > Employees > Employee profile (footer) / History tab
91 | 4. Employee Creation / Change Process | Process | HR creates the employee record | Built | HRMS > Employees | Add Employee from an existing user account
92 | 4. Employee Creation / Change Process | Process | HR imports the employee record (bulk import) | Built | HRMS > Employees | NEW 24 Oct: Employees > Import (CSV / Excel), preview then import; each row runs the same checks as Add Employee and names an existing user account by email.
93 | 4. Employee Creation / Change Process | Process | Duplicate / identity validation before commit | Built | HRMS > Employees | PAN, Aadhaar, UAN, passport, emails, mobile, bank account
94 | 4. Employee Creation / Change Process | Process | Employee ID per configured numbering | Built | HRMS > Employees | DONE 24 Oct: Employee ID format configurable (prefix, year, digits) in Employee Master Setup; default EMP-YYYY-NNN unchanged.
95 | 4. Employee Creation / Change Process | Process | Assign company, department, designation, grade/level, location, reporting manager | Built | HRMS > Employees
96 | 4. Employee Creation / Change Process | Process | Bank, statutory and contact details captured and validated | Built | HRMS > Employees
97 | 4. Employee Creation / Change Process | Process | Effective-dated salary structure and payroll group assigned | Built | HRMS > Employees
98 | 4. Employee Creation / Change Process | Process | Shift, attendance policy, weekly-off and holiday group assigned | Built | HRMS > Employees
99 | 4. Employee Creation / Change Process | Process | Required documents uploaded / verified | Built | HRMS > Employees | Documents module with verification status
100 | 4. Employee Creation / Change Process | Process | Employee activated for Attendance and Payroll | Built | HRMS > Employees | DONE 24 Oct: 'Active for attendance' / 'Active for payroll' switches on the profile; payroll and marking honour them (default on).
101 | 4. Employee Creation / Change Process | Process | Future department/designation/manager/location/salary changes effective-dated; history preserved | Built | HRMS > Employees | Future-dated changes are scheduled and applied on their date
102 | 5. Attendance Configuration | Shift | Shift Code / Name | Built | HRMS > Attendance > Shifts / Holidays / Settings
103 | 5. Attendance Configuration | Shift | Start Time | Built | HRMS > Attendance > Shifts / Holidays / Settings
104 | 5. Attendance Configuration | Shift | End Time | Built | HRMS > Attendance > Shifts / Holidays / Settings
105 | 5. Attendance Configuration | Shift | Break Duration | Built | HRMS > Attendance > Shifts / Holidays / Settings
106 | 5. Attendance Configuration | Shift | Minimum Hours | Built | HRMS > Attendance > Shifts / Holidays / Settings
107 | 5. Attendance Configuration | Grace | Daily Grace Minutes | Built | HRMS > Attendance > Shifts / Holidays / Settings
108 | 5. Attendance Configuration | Grace | Monthly grace / buffer | Built | HRMS > Attendance > Shifts / Holidays / Settings | Built; FRD marks it 'if approved'
109 | 5. Attendance Configuration | Weekly Off | Configured weekday / pattern | Built | HRMS > Attendance > Shifts / Holidays / Settings | Supports e.g. 2nd & 4th Saturday
110 | 5. Attendance Configuration | Holiday Calendar | Holiday Date | Built | HRMS > Attendance > Shifts / Holidays / Settings
111 | 5. Attendance Configuration | Holiday Calendar | Name | Built | HRMS > Attendance > Shifts / Holidays / Settings
112 | 5. Attendance Configuration | Holiday Calendar | Entity / Location applicability | Built | HRMS > Attendance > Shifts / Holidays / Settings | By holiday calendar and location
113 | 5. Attendance Configuration | Attendance Source | Google / API / Biometric / Manual / Import | Built | HRMS > Attendance > Shifts / Holidays / Settings | Client answered 19 Oct (docs/hrms/PHASE1_FRD_GAP_PLAN.md): the source is a label. Manual, Import and Self capture paths built.
114 | 5. Attendance Configuration | Attendance Policy Group | Employee Category; Location; Level; Shift; rule applicability | Built | HRMS > Attendance > Shifts / Holidays / Settings | DONE 24 Oct: Policy Designer scope offers every key: location, department, grade, level, category, shift, policy group, payroll group.
115 | 5. Attendance Configuration | Late Coming | Scheduled In; Grace; Late threshold; late minutes | Built | HRMS > Attendance > Shifts / Holidays / Settings
116 | 5. Attendance Configuration | Early Going | Scheduled Out; permitted grace / threshold | Built | HRMS > Attendance > Shifts / Holidays / Settings
117 | 5. Attendance Configuration | Half Day | Minimum working-hours or policy threshold | Built | HRMS > Attendance > Shifts / Holidays / Settings
118 | 5. Attendance Configuration | Absent | No punch / minimum attendance conditions | Built | HRMS > Attendance > Shifts / Holidays / Settings
119 | 5. Attendance Configuration | Regularisation | Allowed request window | Built | HRMS > Attendance > Shifts / Holidays / Settings
120 | 5. Attendance Configuration | Regularisation | Approval path | Built | HRMS > Attendance > Shifts / Holidays / Settings | Manager then HR
121 | 5. Attendance Configuration | Regularisation | Supporting evidence where required | Built | HRMS > Attendance > Shifts / Holidays / Settings | DONE 24 Oct: evidence can be a file (stored securely, opened by a short-lived link) or a link / reference.
122 | 5. Attendance Configuration | Monthly Cut-off | Attendance closing date | Built | HRMS > Attendance > Shifts / Holidays / Settings | Closing day is enforced when the company turns on 'Enforce the cut-off'; later edits need the lock permission.
123 | 5. Attendance Configuration | Monthly Cut-off | Payroll cut-off | Built | HRMS > Attendance > Shifts / Holidays / Settings | DONE 24 Oct: payroll policy 'Enforce the input cut-off': after the cut-off day only a payroll approver changes inputs (off by default).
124 | 5. Attendance Configuration | Monthly Cut-off | Lock authority | Built | HRMS > Attendance > Shifts / Holidays / Settings | Attendance lock permission
125 | 6. Daily Attendance Fields | Identity | Employee ID | Built | HRMS > Attendance > daily list / day details
126 | 6. Daily Attendance Fields | Identity | Employee Name | Built | HRMS > Attendance > daily list / day details
127 | 6. Daily Attendance Fields | Identity | Department | Built | HRMS > Attendance > daily list / day details
128 | 6. Daily Attendance Fields | Identity | Location | Built | HRMS > Attendance > daily list / day details
129 | 6. Daily Attendance Fields | Date / Schedule | Attendance Date | Built | HRMS > Attendance > daily list / day details
130 | 6. Daily Attendance Fields | Date / Schedule | Day | Built | HRMS > Attendance > daily list / day details
131 | 6. Daily Attendance Fields | Date / Schedule | Shift | Built | HRMS > Attendance > daily list / day details
132 | 6. Daily Attendance Fields | Date / Schedule | Scheduled In | Built | HRMS > Attendance > daily list / day details
133 | 6. Daily Attendance Fields | Date / Schedule | Scheduled Out | Built | HRMS > Attendance > daily list / day details
134 | 6. Daily Attendance Fields | Actual | Actual In | Built | HRMS > Attendance > daily list / day details
135 | 6. Daily Attendance Fields | Actual | Actual Out | Built | HRMS > Attendance > daily list / day details
136 | 6. Daily Attendance Fields | Actual | Attendance source / reference | Built | HRMS > Attendance > daily list / day details
137 | 6. Daily Attendance Fields | Calculated | Worked Hours | Built | HRMS > Attendance > daily list / day details
138 | 6. Daily Attendance Fields | Calculated | Payable Hours | Built | HRMS > Attendance > daily list / day details
139 | 6. Daily Attendance Fields | Calculated | Late Minutes | Built | HRMS > Attendance > daily list / day details
140 | 6. Daily Attendance Fields | Calculated | Early Minutes | Built | HRMS > Attendance > daily list / day details
141 | 6. Daily Attendance Fields | Calculated | Grace Applied | Built | HRMS > Attendance > daily list / day details
142 | 6. Daily Attendance Fields | Status | Present | Built | HRMS > Attendance > daily list / day details
143 | 6. Daily Attendance Fields | Status | Absent | Built | HRMS > Attendance > daily list / day details
144 | 6. Daily Attendance Fields | Status | Half Day | Built | HRMS > Attendance > daily list / day details
145 | 6. Daily Attendance Fields | Status | Weekly Off | Built | HRMS > Attendance > daily list / day details
146 | 6. Daily Attendance Fields | Status | Holiday | Built | HRMS > Attendance > daily list / day details
147 | 6. Daily Attendance Fields | Status | Leave | Built | HRMS > Attendance > daily list / day details
148 | 6. Daily Attendance Fields | Status | OD | Built | HRMS > Attendance > daily list / day details
149 | 6. Daily Attendance Fields | Correction | Regularisation flag | Built | HRMS > Attendance > daily list / day details
150 | 6. Daily Attendance Fields | Correction | Proposed In / Out | Built | HRMS > Attendance > daily list / day details
151 | 6. Daily Attendance Fields | Correction | Reason | Built | HRMS > Attendance > daily list / day details
152 | 6. Daily Attendance Fields | Approval | Manager Status | Built | HRMS > Attendance > daily list / day details
153 | 6. Daily Attendance Fields | Approval | HR Status | Built | HRMS > Attendance > daily list / day details
154 | 6. Daily Attendance Fields | Approval | Approver comments | Built | HRMS > Attendance > daily list / day details
155 | 6. Daily Attendance Fields | Payroll | Final Approved Status | Built | HRMS > Attendance > daily list / day details
156 | 6. Daily Attendance Fields | Payroll | Payable Day | Built | HRMS > Attendance > daily list / day details
157 | 6. Daily Attendance Fields | Payroll | LOP Day / Fraction | Built | HRMS > Attendance > daily list / day details
158 | 6. Daily Attendance Fields | Lock | Locked Flag | Built | HRMS > Attendance > daily list / day details
159 | 6. Daily Attendance Fields | Lock | Locked By | Built | HRMS > Attendance > daily list / day details
160 | 6. Daily Attendance Fields | Lock | Locked Date | Built | HRMS > Attendance > daily list / day details
161 | 6. Daily Attendance Fields | Audit | Original / raw values | Built | HRMS > Attendance > daily list / day details
162 | 6. Daily Attendance Fields | Audit | Corrected values | Built | HRMS > Attendance > daily list / day details
163 | 6. Daily Attendance Fields | Audit | Source and modification history | Built | HRMS > Attendance > daily list / day details
164 | 6. Daily Attendance Fields | Correction | Attachment / evidence | Built | HRMS > Attendance > Regularisation | DONE 24 Oct: regularisation accepts an evidence file attachment.
165 | 8. Attendance Processing & Monthly Closure | Process | Approved OD / leave / regularisation applied before final status | Built | HRMS > Attendance > Monthly Closure / Payroll
166 | 8. Attendance Processing & Monthly Closure | Process | HR resolves pending exceptions at month-end | Built | HRMS > Attendance > Monthly Closure / Payroll | Closure dashboard counts open items
167 | 8. Attendance Processing & Monthly Closure | Process | Payable days and LOP calculated | Built | HRMS > Attendance > Monthly Closure / Payroll
168 | 8. Attendance Processing & Monthly Closure | Process | Attendance snapshot locked | Built | HRMS > Attendance > Monthly Closure / Payroll | Locking with open items needs a reason
169 | 8. Attendance Processing & Monthly Closure | Process | Post-lock changes as authorised adjustments | Built | HRMS > Attendance > Monthly Closure / Payroll | Unlock refused once payroll is locked; arrear / recovery adjustments
170 | 9. Salary Structure Fields | Employee | Employee ID | Built | HRMS > Payroll > Salary Structure
171 | 9. Salary Structure Fields | Employee | Employee Name | Built | HRMS > Payroll > Salary Structure
172 | 9. Salary Structure Fields | Employee | Payroll Group | Built | HRMS > Payroll > Salary Structure
173 | 9. Salary Structure Fields | Effective Dating | Effective From | Built | HRMS > Payroll > Salary Structure
174 | 9. Salary Structure Fields | Effective Dating | Effective To | Built | HRMS > Payroll > Salary Structure | Derived from the next revision
175 | 9. Salary Structure Fields | Effective Dating | Status | Built | HRMS > Payroll > Salary Structure | Pending Approval / Active / Rejected
176 | 9. Salary Structure Fields | Salary Structure | Structure Name / Template | Built | HRMS > Payroll > Salary Structure
177 | 9. Salary Structure Fields | Salary Structure | Revision reason | Built | HRMS > Payroll > Salary Structure
178 | 9. Salary Structure Fields | Annual / Monthly | Annual CTC | Built | HRMS > Payroll > Salary Structure
179 | 9. Salary Structure Fields | Annual / Monthly | Monthly Gross | Built | HRMS > Payroll > Salary Structure
180 | 9. Salary Structure Fields | Earnings | Basic; HRA; approved allowances | Built | HRMS > Payroll > Salary Structure | Configurable components (no fixed list)
181 | 9. Salary Structure Fields | Earnings | Reimbursement | Built | HRMS > Payroll > Salary Structure
182 | 9. Salary Structure Fields | Earnings | Arrears | Built | HRMS > Payroll > Salary Structure | Monthly payroll input
183 | 9. Salary Structure Fields | Earnings | Variable / other earnings | Built | HRMS > Payroll > Salary Structure
184 | 9. Salary Structure Fields | Earnings | Bonus where applicable | Built | HRMS > Payroll > Salary Structure | Monthly payroll input
185 | 9. Salary Structure Fields | Deductions | LOP | Built | HRMS > Payroll > Salary Structure | Applied by proration of earnings on payable days
186 | 9. Salary Structure Fields | Deductions | PF; ESI; PT; TDS | Pending Client Decision | HRMS > Payroll > Salary Structure | PF / ESI / PT / TDS exist as manual inputs and can be set up as components; statutory rules await the client's section 19 decision.
187 | 9. Salary Structure Fields | Deductions | Salary advance recovery | Built | HRMS > Payroll > Salary Structure
188 | 9. Salary Structure Fields | Deductions | Notice / other recovery | Built | HRMS > Payroll > Salary Structure
189 | 9. Salary Structure Fields | Deductions | Other configured deductions | Built | HRMS > Payroll > Salary Structure
190 | 9. Salary Structure Fields | Employer Contributions | Configured employer contribution components | Built | HRMS > Payroll > Salary Structure
191 | 9. Salary Structure Fields | Approval | Created By | Built | HRMS > Payroll > Salary Structure
192 | 9. Salary Structure Fields | Approval | Submitted By | Built | HRMS > Payroll > Salary Structure
193 | 9. Salary Structure Fields | Approval | Approved By | Built | HRMS > Payroll > Salary Structure
194 | 9. Salary Structure Fields | Approval | Approval Date | Built | HRMS > Payroll > Salary Structure
195 | 9. Salary Structure Fields | Approval | Comments | Built | HRMS > Payroll > Salary Structure
196 | 9. Salary Structure Fields | History | Prior structure retained; past payroll cannot be rewritten | Built | HRMS > Payroll > Salary Structure | Structures cannot start inside a locked payroll month
197 | 10. Monthly Payroll Input | Payroll Period | Month; Year; Period Start; Period End | Built | HRMS > Payroll > Payroll Runs
198 | 10. Monthly Payroll Input | Employee | Employee ID; Name; DOJ; LWD if applicable | Built | HRMS > Payroll > Payroll Runs
199 | 10. Monthly Payroll Input | Attendance | Calendar Days; Working Days; Present Days; Payable Days; LOP Days / Fraction; weekly off / holiday counts | Built | HRMS > Payroll > Payroll Runs
200 | 10. Monthly Payroll Input | Salary Basis | Active salary structure and component values | Built | HRMS > Payroll > Payroll Runs
201 | 10. Monthly Payroll Input | Additional Earnings | Reimbursements; Arrears; Variable / Other Earnings; Bonus | Built | HRMS > Payroll > Payroll Runs
202 | 10. Monthly Payroll Input | Recoveries / Deductions | Salary Advance Recovery; Other Recovery; Manual Deduction / Adjustment; statutory / configured deductions | Built | HRMS > Payroll > Payroll Runs
203 | 10. Monthly Payroll Input | Manual Adjustment | Type; Amount; Reason; Source / Reference | Built | HRMS > Payroll > Payroll Runs
204 | 10. Monthly Payroll Input | Manual Adjustment | Approval where needed | Built | HRMS > Payroll > Payroll Runs | DONE 24 Oct: one-off lines above the policy's amount need a second person's approval before submission (off by default).
205 | 10. Monthly Payroll Input | Calculated | Gross Earnings; Total Deductions; Employer Contributions; Net Pay | Built | HRMS > Payroll > Payroll Runs
206 | 10. Monthly Payroll Input | Controls | Exception; Previous Month Net; Variance Amount / %; Maker Status; Checker Status | Built | HRMS > Payroll > Payroll Runs
207 | 11. Payroll Calculation Logic | Formula | Regular + Additional Earnings + Reimbursements + Arrears - LOP - Statutory - Recoveries = Net | Built | HRMS > Payroll > Payroll Runs
208 | 11. Payroll Calculation Logic | Formula | Each component uses its configured rule and source | Built | HRMS > Payroll > Salary Structure | Fixed / % / Formula / Slab / Manual
209 | 11. Payroll Calculation Logic | Formula | Statutory applicability and formulas | Pending Client Decision | - | FRD sections 11 / 19 leave statutory rules to the payroll workshop.
210 | 12. Payroll Approval Workflow | Stage 1 - HR | Finalise attendance exceptions | Built | HRMS > Payroll > Payroll Runs
211 | 12. Payroll Approval Workflow | Stage 2 - HR | Lock monthly attendance snapshot | Built | HRMS > Payroll > Payroll Runs
212 | 12. Payroll Approval Workflow | Stage 3 - Payroll Maker | Open payroll period and load eligible employees | Built | HRMS > Payroll > Payroll Runs
213 | 12. Payroll Approval Workflow | Stage 4 - Payroll Maker | Load salary structures and monthly inputs | Built | HRMS > Payroll > Payroll Runs
214 | 12. Payroll Approval Workflow | Stage 5 - Payroll Maker | Run payroll and review exceptions / variance | Built | HRMS > Payroll > Payroll Runs
215 | 12. Payroll Approval Workflow | Stage 6 - Payroll Maker | Correct permitted inputs and rerun | Built | HRMS > Payroll > Payroll Runs
216 | 12. Payroll Approval Workflow | Stage 7 - Payroll Maker | Submit payroll batch for approval | Built | HRMS > Payroll > Payroll Runs
217 | 12. Payroll Approval Workflow | Stage 8 - Payroll / HR Checker | Verify component values, attendance impact and exceptions | Built | HRMS > Payroll > Payroll Runs | Checker can never be the maker who submitted
218 | 12. Payroll Approval Workflow | Stage 9 - Finance / Authorised Approver | Approve, reject or return payroll | Built | HRMS > Payroll > Payroll Runs | Checker can never be the maker who submitted
219 | 12. Payroll Approval Workflow | Stage 10 - Payroll | Lock approved payroll | Built | HRMS > Payroll > Payroll Runs
220 | 12. Payroll Approval Workflow | Stage 11 - Payroll / Finance | Generate payment file / advice and payslips | Built | HRMS > Payroll > Payroll Runs
221 | 12. Payroll Approval Workflow | Stage 12 - Finance | Process bank salary payment | Built | HRMS > Payroll > Payroll Runs
222 | 12. Payroll Approval Workflow | Stage 13 - Payroll / Finance | Capture UTR / payment status and close payroll period | Built | HRMS > Payroll > Payroll Runs
223 | 13. Salary Disbursal | Field | Payroll Period | Built | HRMS > Payroll > Payroll Runs > Disbursal
224 | 13. Salary Disbursal | Field | Employee ID / Name | Built | HRMS > Payroll > Payroll Runs > Disbursal
225 | 13. Salary Disbursal | Field | Bank / Account / IFSC (masked in UI) | Built | HRMS > Payroll > Payroll Runs > Disbursal | Full number only in the bank file
226 | 13. Salary Disbursal | Field | Net Pay | Built | HRMS > Payroll > Payroll Runs > Disbursal
227 | 13. Salary Disbursal | Field | Payment Mode | Built | HRMS > Payroll > Payroll Runs > Disbursal | NEFT / RTGS / IMPS / Bank Transfer / Cheque / Cash / Manual Advice; no bank API (FRD: later)
228 | 13. Salary Disbursal | Field | Batch Number | Built | HRMS > Payroll > Payroll Runs > Disbursal | PAYB-YYYY-NNN
229 | 13. Salary Disbursal | Field | Generated Date | Built | HRMS > Payroll > Payroll Runs > Disbursal
230 | 13. Salary Disbursal | Field | Payment Date | Built | HRMS > Payroll > Payroll Runs > Disbursal
231 | 13. Salary Disbursal | Field | Payment Status (Pending / Processed / Failed / Rejected) | Built | HRMS > Payroll > Payroll Runs > Disbursal
232 | 13. Salary Disbursal | Field | UTR / Transaction Reference | Built | HRMS > Payroll > Payroll Runs > Disbursal | Manual entry or bank-response import
233 | 13. Salary Disbursal | Field | Failure Reason | Built | HRMS > Payroll > Payroll Runs > Disbursal
234 | 13. Salary Disbursal | Field | Retry Batch | Built | HRMS > Payroll > Payroll Runs > Disbursal
235 | 14. Payslip | Employee Header | Employee ID; Name; Designation; Department; Payroll Month; approved identifiers | Built | HRMS > Payroll > Payslip | PAN / bank masked
236 | 14. Payslip | Attendance | Payable Days; LOP Days | Built | HRMS > Payroll > Payslip | LOP days shown if template allows
237 | 14. Payslip | Regular Earnings | Basic; HRA; regular allowances | Built | HRMS > Payroll > Payslip
238 | 14. Payslip | Other Earnings | Reimbursement; Arrears; Variable Pay / Incentive; Bonus; Other Earnings | Built | HRMS > Payroll > Payslip
239 | 14. Payslip | Deductions | PF; ESI; PT; TDS; Salary Advance Recovery; Other Recovery / Deductions | Built | HRMS > Payroll > Payslip
240 | 14. Payslip | Deductions | LOP (as a deduction line) | Built | HRMS > Payroll > Payslip | DONE 24 Oct: payslip template option 'Show LOP as a deduction line' (earnings at full amount, one LOP line, same net pay).
241 | 14. Payslip | Totals | Gross Earnings; Total Deductions; Net Pay | Built | HRMS > Payroll > Payslip | Plus net pay in words
242 | 14. Payslip | Template | Sparsh-approved format; version retained per payroll period | Pending Client Decision | HRMS > Payroll > Payslip | Template versioning and per-period freeze built; the Sparsh-approved format is still to come (section 19).
243 | 14. Payslip | Release | Only after final approval / lock | Built | HRMS > Payroll > Payslip | Release on lock or after payment (policy setting)
244 | 16. Core Data Relationships | Relationship | Employee -> multiple effective-dated Salary Structures | Built | Backend data model
245 | 16. Core Data Relationships | Relationship | Salary Structure -> Component Lines | Built | Backend data model
246 | 16. Core Data Relationships | Relationship | Employee -> Attendance Event / Day | Built | Backend data model
247 | 16. Core Data Relationships | Relationship | Attendance Day -> Regularisation | Built | Backend data model
248 | 16. Core Data Relationships | Relationship | Attendance Month Lock -> Payroll Period | Built | Backend data model
249 | 16. Core Data Relationships | Relationship | Payroll Period + Employee -> Payroll Input | Built | Backend data model
250 | 16. Core Data Relationships | Relationship | Payroll Result -> Result Lines | Built | Backend data model
251 | 16. Core Data Relationships | Relationship | Payroll Period -> Approval Steps | Built | Backend data model
252 | 16. Core Data Relationships | Relationship | Payroll Result -> Payslip | Built | Backend data model
253 | 16. Core Data Relationships | Relationship | Payroll Period -> Bank Batch -> Bank Payment | Built | Backend data model
254 | 16. Core Data Relationships | Relationship | Critical Entities -> Audit Log | Built | Backend data model
255 | 17. Roles & Access | Role | Employee: own profile, attendance calendar, late-coming, regularisation, final payslip | Built | HRMS permissions
256 | 17. Roles & Access | Role | Reporting Manager: team attendance; approve regularisation / OD | Built | HRMS permissions | Manager step only; HR gives final sign-off
257 | 17. Roles & Access | Role | HR: employee records, attendance configuration, exceptions, attendance lock | Built | HRMS permissions
258 | 17. Roles & Access | Role | Payroll Maker: salary structures, inputs, calculate, submit | Built | HRMS permissions
259 | 17. Roles & Access | Role | Payroll / HR Checker: review calculations, exceptions, variance | Built | HRMS permissions | Separate Check permission, run status and endpoint; HR checks, Finance approves; checker differs from maker and approver.
260 | 17. Roles & Access | Role | Finance / Authorised Approver: final approval and payment controls | Built | HRMS permissions
261 | 17. Roles & Access | Role | System Admin: no automatic entitlement to payroll-sensitive values | Built | HRMS permissions | DONE 24 Oct: Roles & Permissions switch: superadmin sees payroll values only when explicitly granted (off by default to keep current access). Platform admin role never had payroll access.
262 | 18. Validation & Control Requirements | Control | Employee duplication checked before creating a record | Built | System-wide
263 | 18. Validation & Control Requirements | Control | Sensitive bank, statutory and salary fields restricted | Built | System-wide
264 | 18. Validation & Control Requirements | Control | Salary structures and organisation / reporting changes effective-dated | Built | System-wide
265 | 18. Validation & Control Requirements | Control | Raw attendance traceable after regularisation | Built | System-wide
266 | 18. Validation & Control Requirements | Control | Attendance locked before payroll is finalised | Built | System-wide
267 | 18. Validation & Control Requirements | Control | Payroll uses the locked attendance snapshot | Built | System-wide
268 | 18. Validation & Control Requirements | Control | Exception reporting and previous-month variance | Built | System-wide
269 | 18. Validation & Control Requirements | Control | Maker-checker approval mandatory before payroll lock | Built | System-wide
270 | 18. Validation & Control Requirements | Control | Locked payroll not edited in place (adjustment / arrear / reversal) | Built | System-wide
271 | 18. Validation & Control Requirements | Control | Bank file only from approved / locked payroll | Built | System-wide
272 | 18. Validation & Control Requirements | Control | Payment status and UTR retained per employee / batch | Built | System-wide
273 | 18. Validation & Control Requirements | Control | Payslip reflects component values used in final payroll | Built | System-wide
274 | 18. Validation & Control Requirements | Control | Audit trail for create / update / approve / reject / lock / payment | Built | System-wide
275 | 20. Phase 1 Acceptance Criteria | Criterion | HR can create an employee with organisation, reporting, attendance and payroll linkage | Built | Tested end-to-end on a copy of the data
276 | 20. Phase 1 Acceptance Criteria | Criterion | Employee changes preserve history | Built | Tested end-to-end on a copy of the data
277 | 20. Phase 1 Acceptance Criteria | Criterion | Daily attendance calculates status, hours and late-coming | Built | Tested end-to-end on a copy of the data
278 | 20. Phase 1 Acceptance Criteria | Criterion | Employees / Managers complete the regularisation flow | Built | Tested end-to-end on a copy of the data
279 | 20. Phase 1 Acceptance Criteria | Criterion | HR resolves exceptions, calculates payable days / LOP and locks attendance | Built | Tested end-to-end on a copy of the data
280 | 20. Phase 1 Acceptance Criteria | Criterion | Payroll loads the locked attendance and current salary structure | Built | Tested end-to-end on a copy of the data
281 | 20. Phase 1 Acceptance Criteria | Criterion | Payroll accepts reimbursement, arrears, other earnings and recovery inputs | Built | Tested end-to-end on a copy of the data
282 | 20. Phase 1 Acceptance Criteria | Criterion | Payroll calculates gross, deductions, employer contributions and net component-wise | Built | Tested end-to-end on a copy of the data
283 | 20. Phase 1 Acceptance Criteria | Criterion | Maker reviews exceptions / variance, corrects and reruns | Built | Tested end-to-end on a copy of the data
284 | 20. Phase 1 Acceptance Criteria | Criterion | Checker / Finance can approve, reject or return | Built | Tested end-to-end on a copy of the data
285 | 20. Phase 1 Acceptance Criteria | Criterion | Approved payroll is locked and cannot be edited | Built | Tested end-to-end on a copy of the data
286 | 20. Phase 1 Acceptance Criteria | Criterion | System generates payroll register, payslips and bank payment output | Built | Tested end-to-end on a copy of the data
287 | 20. Phase 1 Acceptance Criteria | Criterion | Finance captures batch, UTR and success / failure status | Built | Tested end-to-end on a copy of the data
288 | 20. Phase 1 Acceptance Criteria | Criterion | Employee receives the final approved payslip | Built | Tested end-to-end on a copy of the data
289 | 21. Cross-Module Configurability | Capability | Employee Fields: add / relabel / mandatory / show-hide / order / dropdowns / retire | Built | HRMS > Employee Master Setup / Attendance / Payroll | Configurable fields
290 | 21. Cross-Module Configurability | Capability | Attendance Fields: operational fields and flags; display, validation, source mapping | Built | HRMS > Employee Master Setup / Attendance / Payroll | DONE 24 Oct: attendance fields can name an import-file column (source mapping); the biometric import fills them.
291 | 21. Cross-Module Configurability | Capability | Attendance Rules / Policy by effective date | Built | HRMS > Employee Master Setup / Attendance / Payroll | Daily rules, regularisation and closure are effective-dated policy versions resolved per employee per date.
292 | 21. Cross-Module Configurability | Capability | Salary Components: create / modify / deactivate without code deployment | Built | HRMS > Employee Master Setup / Attendance / Payroll
293 | 21. Cross-Module Configurability | Capability | Payroll Calculations: formulas, conditions, slab / % / fixed, calculation sequence | Built | HRMS > Employee Master Setup / Attendance / Payroll
294 | 21. Cross-Module Configurability | Capability | Payroll Policy: cut-off, eligibility, applicability, rounding, approval controls with versioning | Built | HRMS > Employee Master Setup / Attendance / Payroll | DONE 24 Oct: eligibility (categories left out), cut-off enforcement, approval matrix from the screen (was dropped), versioning, scope.
295 | 21. Cross-Module Configurability | Capability | Payslip Layout Mapping: components to sections; hide zero; retain template per period | Built | HRMS > Employee Master Setup / Attendance / Payroll
296 | 21. Cross-Module Configurability | Capability | Used items retired / deactivated, never physically deleted | Built | HRMS > Employee Master Setup / Attendance / Payroll | Fields and components retire
297 | 22. Configurable Field Management | Identity | Module, Section, Field Code, Label, Help Text | Built | HRMS > Employee Master Setup > Configurable fields
298 | 22. Configurable Field Management | Data Type | Text, Long Text, Number, Decimal, Currency, Date, Date-Time, Yes/No, Single Select, Multi Select | Built | HRMS > Employee Master Setup > Configurable fields
299 | 22. Configurable Field Management | Data Type | Employee Lookup, Master Lookup, File / Document reference | Built | HRMS > Employee Master Setup > Configurable fields | Profile form offers an employee picker, a master-list dropdown and a document-reference input.
300 | 22. Configurable Field Management | Behaviour | Mandatory / Optional, Read-only, Default Value, Unique | Built | HRMS > Employee Master Setup > Configurable fields
301 | 22. Configurable Field Management | Behaviour | Searchable, Filterable, Exportable | Built | HRMS > Employee Master Setup > Configurable fields | DONE 24 Oct: Searchable fields are matched by directory search; Filterable fields become directory filters; Exportable honoured by export.
302 | 22. Configurable Field Management | Visibility | Role-based; self-service; manager; HR / payroll | Built | HRMS > Employee Master Setup > Configurable fields
303 | 22. Configurable Field Management | Validation | Min / max length & value, regex, date range, custom message | Built | HRMS > Employee Master Setup > Configurable fields
304 | 22. Configurable Field Management | Validation | Dependent validation | Built | HRMS > Employee Master Setup > Configurable fields | NEW 24 Oct: 'Required when' / 'Allowed only when' another custom or profile field holds given values.
305 | 22. Configurable Field Management | Dropdown / Lookup | Option values, sequence, active / inactive, source master | Built | HRMS > Employee Master Setup > Configurable fields
306 | 22. Configurable Field Management | Applicability | Company, location, department, grade/level, category, payroll group, effective date | Built | HRMS > Employee Master Setup > Configurable fields | DONE 24 Oct: applicability editor (location, grade, level, category, payroll group, department) in the field editor.
307 | 22. Configurable Field Management | Display | Section / tab, display order | Built | HRMS > Employee Master Setup > Configurable fields
308 | 22. Configurable Field Management | Display | Grid / list visibility | Built | HRMS > Employee Master Setup > Configurable fields | DONE 24 Oct: 'Show in list' fields appear as directory columns (sensitive ones never).
309 | 22. Configurable Field Management | Lifecycle | Draft, Active, Retired; Effective From / To | Built | HRMS > Employee Master Setup > Configurable fields
310 | 22. Configurable Field Management | Lifecycle | Approved (separate state) | Built | HRMS > Employee Master Setup > Configurable fields | NEW 24 Oct: Draft -> Approved (by someone other than the author) -> Active; under the section 27 flow the request's approval sets Approved.
311 | 22. Configurable Field Management | Audit | Created by/on, approved by/on, change reason, old / new definition | Built | HRMS > Employee Master Setup > Configurable fields
312 | 22. Configurable Field Management | Control | Label / order change does not alter stored values | Built | HRMS > Employee Master Setup > Configurable fields
313 | 22. Configurable Field Management | Control | Data type change blocked once values exist | Built | HRMS > Employee Master Setup > Configurable fields
314 | 22. Configurable Field Management | Control | Field used in a calculation cannot be retired | Built | HRMS > Employee Master Setup > Configurable fields | NEW 24 Oct: retiring a field is refused while a bank file column or policy scope reads it. Formulas cannot read custom fields, so no calculation depends on one.
315 | 22. Configurable Field Management | Control | Mandatory applies from an effective date | Built | HRMS > Employee Master Setup > Configurable fields
316 | 22. Configurable Field Management | Control | Field-level permissions for sensitive fields | Built | HRMS > Employee Master Setup > Configurable fields
317 | 23. Attendance Policy & Rule Configuration | Engine | Versioned rules; future effective date; prior periods unchanged | Built | HRMS > Attendance > Shifts / Settings | Shift versions; locked months never rewritten
318 | 23. Attendance Policy & Rule Configuration | Engine | Test a policy version before activation | Built | HRMS > Attendance > Shifts / Settings | A draft daily-rules version is simulated against recorded punches, old vs proposed, writing nothing.
319 | 23. Attendance Policy & Rule Configuration | Shift / Timing | Start, end, break, minimum hours, flexible timing, applicability | Built | HRMS > Attendance > Shifts / Settings
320 | 23. Attendance Policy & Rule Configuration | Late Coming | Grace, threshold, late-minute calculation, monthly buffer | Built | HRMS > Attendance > Shifts / Settings
321 | 23. Attendance Policy & Rule Configuration | Late Coming | Escalation threshold | Built | HRMS > Attendance > Shifts / Settings | NEW 24 Oct: ATT_DAY rule 'Escalate at late days / month'; the late-coming card flags people who reach it.
322 | 23. Attendance Policy & Rule Configuration | Early Going | Threshold, grace and treatment | Built | HRMS > Attendance > Shifts / Settings
323 | 23. Attendance Policy & Rule Configuration | Half Day | Working-hour threshold | Built | HRMS > Attendance > Shifts / Settings
324 | 23. Attendance Policy & Rule Configuration | Half Day | Late / early combinations; approved exception treatment | Built | HRMS > Attendance > Shifts / Settings | DONE 24 Oct: half-day combinations plus 'approved exception treatment': named approved request types waive a late / early half day.
325 | 23. Attendance Policy & Rule Configuration | Absent | No-punch / minimum-hours conditions | Built | HRMS > Attendance > Shifts / Settings
326 | 23. Attendance Policy & Rule Configuration | Weekly Off / Holiday | Patterns, location calendar, holiday treatment | Built | HRMS > Attendance > Shifts / Settings
327 | 23. Attendance Policy & Rule Configuration | OD / Regularisation | Request types, window, evidence requirement | Built | HRMS > Attendance > Shifts / Settings
328 | 23. Attendance Policy & Rule Configuration | OD / Regularisation | Manager / HR approval levels (configurable) | Built | HRMS > Attendance > Shifts / Settings | Approval levels (1 = manager, 2 = manager then HR) resolved per request and enforced.
329 | 23. Attendance Policy & Rule Configuration | LOP | Source status, fraction / full-day, leave interaction | Built | HRMS > Attendance > Shifts / Settings | Plus optional 'sandwich' rule
330 | 23. Attendance Policy & Rule Configuration | Monthly Closure | Cut-off date, pending-request handling, lock / unlock authority | Built | HRMS > Attendance > Shifts / Settings | DONE 24 Oct: 'Block locking with open requests' is enforced at lock; cut-off and lock / unlock authority as before.
331 | 23. Attendance Policy & Rule Configuration | Applicability | Company, location, department, category, grade, shift group, effective dates | Built | HRMS > Attendance > Shifts / Settings
332 | 23. Attendance Policy & Rule Configuration | Applicability | Level | Built | HRMS > Attendance > Shifts / Settings | DONE 24 Oct: Level is offered in the Policy Designer scope.
333 | 24. Salary Component Configuration | Component Type | Earning, Deduction, Employer Contribution, Reimbursement, Recovery, Informational | Built | HRMS > Payroll > Salary Structure > Component editor
334 | 24. Salary Component Configuration | Calculation Method | Fixed, Percentage, Formula, Manual Input, Slab / Table | Built | HRMS > Payroll > Salary Structure > Component editor
335 | 24. Salary Component Configuration | Calculation Method | Imported Input | Built | HRMS > Payroll > Salary Structure > Component editor | DONE 24 Oct: Imported Input values uploaded per payroll run (employee, component, amount); recalculation required before submit.
336 | 24. Salary Component Configuration | Calculation Method | Attendance-linked | Built | HRMS > Payroll > Salary Structure > Component editor | Rate x attendance quantity from the frozen attendance basis.
337 | 24. Salary Component Configuration | Calculation Base | Basic, Gross, CTC, another component | Built | HRMS > Payroll > Salary Structure > Component editor
338 | 24. Salary Component Configuration | Calculation Base | Payable days / statutory base / configurable expression | Built | HRMS > Payroll > Salary Structure > Component editor | Component / Gross / CTC bases; formulas read payable days, LOP and components.
339 | 24. Salary Component Configuration | Frequency | Monthly, one-time, quarterly, annual, ad hoc | Built | HRMS > Payroll > Salary Structure > Component editor | Quarterly / annual enforced from the start date; one-time / ad hoc paid as run adjustments.
340 | 24. Salary Component Configuration | Proration | Full month, payable-days based | Built | HRMS > Payroll > Salary Structure > Component editor
341 | 24. Salary Component Configuration | Proration | Working-days based | Built | HRMS > Payroll > Salary Structure > Component editor | Working-days proration: payable working days / working days.
342 | 24. Salary Component Configuration | Applicability | Employee / category / grade / location / payroll group and effective dates | Built | HRMS > Payroll > Salary Structure > Component editor | Applicability by location, grade, category, payroll group and effective dates, checked per employee per run.
343 | 24. Salary Component Configuration | Rounding | None, nearest, floor, ceiling | Built | HRMS > Payroll > Salary Structure > Component editor
344 | 24. Salary Component Configuration | Minimum / Maximum | Optional cap / floor | Built | HRMS > Payroll > Salary Structure > Component editor
345 | 24. Salary Component Configuration | Sequence | Calculation priority / order | Built | HRMS > Payroll > Salary Structure > Component editor
346 | 24. Salary Component Configuration | Payslip Mapping | Regular, Other, Deductions, Employer Contribution, Hidden | Built | HRMS > Payroll > Salary Structure > Component editor
347 | 24. Salary Component Configuration | Accounting / Bank Mapping | Optional code for export | Built | HRMS > Payroll > Salary Structure > Component editor
348 | 24. Salary Component Configuration | Lifecycle | Draft, Approved, Active, Superseded, Retired | Built | HRMS > Payroll > Salary Structure > Component editor | DONE 24 Oct: Draft -> Approved (on approval) -> Active (on activation) -> Superseded (previous version kept) / Retired; live components revised only through approval.
349 | 25. Formula / Calculation Rule Engine | Variables | Prior calculated components, constants, GROSS, CTC | Built | HRMS > Payroll > Salary Structure > Component editor
350 | 25. Formula / Calculation Rule Engine | Variables | Employee fields, attendance / payable days / LOP, payroll inputs | Built | HRMS > Payroll > Salary Structure > Component editor | Employee (EMP_*), attendance, structure, constants and earlier components; NEW 24 Oct: payroll inputs (INPUT_*). Custom fields are not variables.
351 | 25. Formula / Calculation Rule Engine | Operators | Arithmetic, comparison, AND / OR, MIN, MAX, ROUND, FLOOR, CEIL, ABS | Built | HRMS > Payroll > Salary Structure > Component editor | No arbitrary code can run
352 | 25. Formula / Calculation Rule Engine | Conditions | IF / ELSE eligibility and thresholds | Built | HRMS > Payroll > Salary Structure > Component editor
353 | 25. Formula / Calculation Rule Engine | Formula Versioning | Version number and change history | Built | HRMS > Payroll > Salary Structure > Component editor
354 | 25. Formula / Calculation Rule Engine | Formula Versioning | Effective dates, status and approval per formula version | Built | HRMS > Payroll > Salary Structure > Component editor | DONE 24 Oct: a formula revision is staged, approved, then activated as a new version; the old version is kept as Superseded.
355 | 25. Formula / Calculation Rule Engine | Dependency Validation | Prevent circular dependencies; list affected components | Built | HRMS > Payroll > Salary Structure > Component editor
356 | 25. Formula / Calculation Rule Engine | Simulation | Test against employees before activation | Built | HRMS > Payroll > Salary Structure > Component editor | Component 'Simulate change'
357 | 25. Formula / Calculation Rule Engine | Comparison | Old result vs proposed rule | Built | HRMS > Payroll > Salary Structure > Component editor
358 | 25. Formula / Calculation Rule Engine | Audit | Formula / component version stored on each payroll result | Built | HRMS > Payroll > Salary Structure > Component editor
359 | 25. Formula / Calculation Rule Engine | Failure Handling | Calculation errors block approval | Built | HRMS > Payroll > Salary Structure > Component editor | Critical exceptions block submission
360 | 26. Policy Versioning & Effective Dates | Rule | Every material policy change creates a new version | Built | HRMS > Employee Master Setup / Attendance / Payroll | DONE 24 Oct: every save of the company attendance rules is a numbered version with old / new values, author, reason and effective date.
361 | 26. Policy Versioning & Effective Dates | Rule | Effective From and Effective To | Built | HRMS > Employee Master Setup / Attendance / Payroll | DONE 24 Oct: Effective To can be set in the Policy Designer and the Payroll Policy screen.
362 | 26. Policy Versioning & Effective Dates | Rule | Scope by company, location, department, grade, category, shift, payroll group | Built | HRMS > Employee Master Setup / Attendance / Payroll | DONE 24 Oct: all scope keys in the Policy Designer; Payroll Policy screen scopes by location, grade, category and payroll group.
363 | 26. Policy Versioning & Effective Dates | Rule | Priority / specificity rule when several policies match | Built | HRMS > Employee Master Setup / Attendance / Payroll | Employee shift > most specific match > company timing
364 | 26. Policy Versioning & Effective Dates | Rule | Historical records keep the version used | Built | HRMS > Employee Master Setup / Attendance / Payroll
365 | 26. Policy Versioning & Effective Dates | Rule | Retroactive change needs an authorised process | Built | HRMS > Employee Master Setup / Attendance / Payroll | Back-dating needs a reason and cannot enter locked months
366 | 26. Policy Versioning & Effective Dates | Rule | Draft preview / simulation before activation | Built | HRMS > Employee Master Setup / Attendance / Payroll | DONE 24 Oct: previews for regularisation, closure and payroll policy drafts as well as daily rules and components.
367 | 27. Configuration Change Approval Flow | Stage | Request (change and business reason) | Built | HRMS > Employee Master Setup / Attendance / Payroll | Change request with a mandatory business reason, requester and timestamp.
368 | 27. Configuration Change Approval Flow | Stage | Draft | Built | HRMS > Employee Master Setup / Attendance / Payroll | DONE 24 Oct: an Active component / formula revision is held as a draft until approved and activated.
369 | 27. Configuration Change Approval Flow | Stage | Impact Analysis | Built | HRMS > Employee Master Setup / Attendance / Payroll | DONE 24 Oct: impact analysis lists the open and closed attendance / payroll periods the change reaches.
370 | 27. Configuration Change Approval Flow | Stage | Test / Simulation | Built | HRMS > Employee Master Setup / Attendance / Payroll | DONE 24 Oct: simulation runs from the request (Approval Inbox and Policy Designer) and is recorded on it.
371 | 27. Configuration Change Approval Flow | Stage | Approval (approve / reject / return) | Built | HRMS > Employee Master Setup / Attendance / Payroll | Approve / reject / return with comments; the requester cannot approve; Approval Inbox in the sidebar.
372 | 27. Configuration Change Approval Flow | Stage | Effective Dating | Built | HRMS > Employee Master Setup / Attendance / Payroll
373 | 27. Configuration Change Approval Flow | Stage | Activation | Built | HRMS > Employee Master Setup / Attendance / Payroll
374 | 27. Configuration Change Approval Flow | Stage | Runtime uses active version | Built | HRMS > Employee Master Setup / Attendance / Payroll
375 | 27. Configuration Change Approval Flow | Stage | History immutable | Built | HRMS > Employee Master Setup / Attendance / Payroll
376 | 29. Administrative Screens | Screen | Employee Field Configuration | Built | HRMS | Employee Master Setup
377 | 29. Administrative Screens | Screen | Attendance Field Configuration | Built | HRMS | Employee Master Setup (Attendance module)
378 | 29. Administrative Screens | Screen | Attendance Policy Designer | Built | HRMS | Attendance > Shifts / Settings
379 | 29. Administrative Screens | Screen | Salary Component Master | Built | HRMS | Payroll > Salary Structure
380 | 29. Administrative Screens | Screen | Payroll Formula Designer | Built | HRMS | Component editor (Formula / Slab)
381 | 29. Administrative Screens | Screen | Policy Version & Scope | Built | HRMS | DONE 24 Oct: versions, effective dates and full scope in the Policy Designer; versions, Effective To and scope on Payroll Policy.
382 | 29. Administrative Screens | Screen | Configuration Impact / Dependency Viewer | Built | HRMS | Audit & Impact screen shows where a field, component or policy is used.
383 | 29. Administrative Screens | Screen | Rule Simulation | Built | HRMS | DONE 24 Oct: Rule Simulation tab on Configuration Audit & Impact (any policy version or component, chosen employees, any month).
384 | 29. Administrative Screens | Screen | Configuration Approval Inbox | Built | HRMS | Approval Inbox screen is routed and in the sidebar.
385 | 29. Administrative Screens | Screen | Configuration Audit Viewer | Built | HRMS | Lists requester, approver, reason, decision trail and old / new definition, exportable; covers changes made through the approval flow.
386 | 30. Configurability Acceptance Criteria | Criterion | HR adds an Employee Master field without code deployment | Built | HRMS > Employee Master Setup / Attendance / Payroll
387 | 30. Configurability Acceptance Criteria | Criterion | Admin changes label, visibility, mandatory, validation, dropdowns | Built | HRMS > Employee Master Setup / Attendance / Payroll
388 | 30. Configurability Acceptance Criteria | Criterion | Used fields retired, not deleted | Built | HRMS > Employee Master Setup / Attendance / Payroll
389 | 30. Configurability Acceptance Criteria | Criterion | Future-dated attendance policy applied to a selected population | Built | HRMS > Employee Master Setup / Attendance / Payroll
390 | 30. Configurability Acceptance Criteria | Criterion | Late / half-day change does not recalculate closed periods | Built | HRMS > Employee Master Setup / Attendance / Payroll
391 | 30. Configurability Acceptance Criteria | Criterion | Payroll adds a component and configures calculation / payslip mapping | Built | HRMS > Employee Master Setup / Attendance / Payroll
392 | 30. Configurability Acceptance Criteria | Criterion | Formula revised as a new version, simulated and approved before activation | Built | HRMS > Employee Master Setup / Attendance / Payroll | DONE 24 Oct: component edits go through request -> impact -> simulation -> approval -> activation.
393 | 30. Configurability Acceptance Criteria | Criterion | Circular dependencies prevented | Built | HRMS > Employee Master Setup / Attendance / Payroll
394 | 30. Configurability Acceptance Criteria | Criterion | Payroll result records rule / component versions | Built | HRMS > Employee Master Setup / Attendance / Payroll
395 | 30. Configurability Acceptance Criteria | Criterion | Configuration changes audited with requester, approver, reason, date, old / new | Partially Built | HRMS > Employee Master Setup / Attendance / Payroll | Full record (requester, approver, reason, date, old / new) for everything through the approval flow, now including salary components. The company attendance-rules screen and fields outside the approval flow record author, reason and old / new but no approver.
396 | 30. Configurability Acceptance Criteria | Criterion | Impact / dependency check before retirement | Built | HRMS > Employee Master Setup / Attendance / Payroll | Impact check for fields, components and policies; retirement is blocked for components and (NEW 24 Oct) fields.
397 | 30. Configurability Acceptance Criteria | Criterion | Configuration access separate from employee / manager access | Built | HRMS > Employee Master Setup / Attendance / Payroll

## Missing & Partial Report
Report: fields not fully built (Missing, then Partially Built, then Pending Client Decision)
# | Build Status | FRD Section | Group | Field / Requirement | Gap
1 | Partially Built | 30. Configurability Acceptance Criteria | Criterion | Configuration changes audited with requester, approver, reason, date, old / new | Full record (requester, approver, reason, date, old / new) for everything through the approval flow, now including salary components. The company attendance-rules screen and fields outside the approval flow record author, reason and old / new but no approver.
2 | Pending Client Decision | 9. Salary Structure Fields | Deductions | PF; ESI; PT; TDS | PF / ESI / PT / TDS exist as manual inputs and can be set up as components; statutory rules await the client's section 19 decision.
3 | Pending Client Decision | 11. Payroll Calculation Logic | Formula | Statutory applicability and formulas | FRD sections 11 / 19 leave statutory rules to the payroll workshop.
4 | Pending Client Decision | 14. Payslip | Template | Sparsh-approved format; version retained per payroll period | Template versioning and per-period freeze built; the Sparsh-approved format is still to come (section 19).

## Missing Values (FRD)
Values the FRD itself leaves undefined - to be confirmed by Sparsh Magic (nothing filled in by assumption)
# | FRD Section | Item | What the FRD says | Missing Value | Value (to be filled by client)
1 | 19 | Employee Categories | Final list and applicability | Not provided in the FRD
2 | 19 | Attendance Source | Google, biometric, API, manual/import or combination | Not in the FRD. Repo note says the client answered on 19 Oct: source is a label, no integration
3 | 19 | Late / Half-Day / LOP Rules | Exact thresholds after grace / buffer | Not provided in the FRD
4 | 19 | Monthly Attendance Cut-off | Date and unlock authority | Not provided in the FRD
5 | 19 | Salary Components | Complete earning, deduction and employer-contribution catalogue | Not provided in the FRD
6 | 19 | Statutory Applicability | PF / ESI / PT / TDS and entity / location rules | Not provided in the FRD
7 | 19 | Payroll Approval Matrix | Exact maker / checker / finance approvers | Not provided in the FRD
8 | 19 | Bank File Format | Bank-specific layout and mandatory fields | Not provided in the FRD
9 | 19 | Payslip Format | Final approved Sparsh Magic payslip template | Not provided in the FRD
10 | 19 | Payslip Release | Immediate after approval or after confirmed bank processing | Not decided in the FRD
11 | 19 | Payment Failure Process | Owner and retry / reversal procedure | Not provided in the FRD
12 | 1 / 11 | Statutory formulas (PF, ESI, PT, TDS) | Subject to payroll workshop | Not provided in the FRD
13 | 3 | Other approved statutory identifiers | List of identifiers | Not listed in the FRD
14 | 3 | Documents - 'other approved categories' | List of categories | Not listed in the FRD
15 | 3 | Documents - 'PSC' | Meaning / definition of PSC | Not defined in the FRD
16 | 5 | Monthly grace / buffer | Marked 'if approved' | Approval not stated
17 | 5 | Attendance Source | 'final source to be confirmed' | Not in the FRD. Repo note says the client answered on 19 Oct: source is a label, no integration
18 | 9 / 10 | Bonus | 'where applicable' - applicability rule | Not defined in the FRD
19 | 14 | LOP Days on payslip | 'if part of final approved format' | Not decided
20 | 14 | Payslip release policy | 'subject to final release policy' | Not provided
21 | Cover | Document date | Prepared Date 12 Oct 2026 vs footer 14 Oct 2026 | Two different dates in the document
22 | 15 | ER Diagram (page 8) | Page 8 carries only the caption; the diagram is on page 7 | Page 8 body empty

## Defects Found
Defects in existing code found by the 24 Oct re-audit
# | Defect | FRD Sections | What happens | Status
1 | Salary component approval not enforced | 24 Lifecycle; 25 Formula Versioning; 27 Draft; 30 | Salary components are governed by default, but the component save never checked it, so the Component Editor changed a live formula or set lifecycle Active with no approval. | FIXED 24 Oct: live revisions are staged and go through the approval flow.
2 | Payroll Policy screen's approval settings dropped | 21 Payroll Policy; 12 approval matrix | PayrollPolicy.jsx sent checker_required, approver_distinct_from_checker and lock_cap; PayrollPolicyIn had no such fields, so they were silently discarded. | FIXED 24 Oct: the request model accepts them.
3 | Regularisation request type dropped | 23 OD / Regularisation request types | The service validates request_type against the configured types, but RegularizationIn had no such field, so with types configured every request was refused. | FIXED 24 Oct: the request model and form carry the request type.
4 | Drafted change requests could not be sent for approval | 27 Request -> Approval | Payroll Policy, field and component changes create a Draft request, and no screen could analyse, simulate or submit it -- the approver only sees Pending Approval. | FIXED 24 Oct: the Approval Inbox lets the drafter run simulation and send for approval.